## RHEL9_Cutover_DevOps_Plan
Phase | Task ID | Task Description | Business Group | Environment | Owner | Pre-Check Required (Y/N) | Execution Time (Planned) | Status | Validation Steps | Rollback Plan | Remarks
Pre-Cutover | 1.1 | Validate Application Property Files in /apps/shapp/<BG>/propertyFiles/ | All 23 BGs | Dev/QA/Prod | DevOps | Y |  | Pending | Compare against baseline; validate secure properties; confirm Delinea sync | Restore previous property backup from NFS
Pre-Cutover | 1.2 | Validate Shared Properties in /apps/shapp/shared-properties/ | Shared | Dev/QA/Prod | DevOps | Y |  | Pending | Checksum validation; confirm no missing keys | Restore shared backup snapshot
Pre-Cutover | 1.3 | Certificate Placement Validation (Keystore/Truststore) | All 23 BGs | Dev/QA/Prod | DevOps | Y |  | Pending | Validate alias using keytool -list; confirm expiry date; confirm path in wrapper.conf | Re-import previous cert from backup
Pre-Cutover | 1.4 | Runtime 4.3 Status Validation | All 23 BGs | RHEL 7 | DevOps | Y |  | Pending | Check systemctl status mule.<bg>.service; verify heap usage | N/A
Cutover | 2.1 | Stop All Applications in Runtime 4.3 | All 23 BGs | RHEL 7 | DevOps | Y |  | Pending | Verify app status stopped in Runtime Manager | Restart applications if rollback required
Cutover | 2.2 | Stop Mule Runtime 4.3 | All 23 BGs | RHEL 7 | DevOps | Y |  | Pending | sudo systemctl stop mule.<bg>.service | sudo systemctl start mule.<bg>.service
Cutover | 2.3 | Start Mule Runtime 4.9 (RHEL 9) | All 23 BGs | RHEL 9 | DevOps | Y |  | Pending | sudo systemctl start mule.<bg>.service; confirm logs clean | Stop 4.9 and restart 4.3
Cutover | 2.4 | Deploy 23 Applications to Runtime 4.9 | All 23 BGs | RHEL 9 | DevOps | Y |  | Pending | Monitor deployment logs; verify ports; healthcheck endpoints | Redeploy previous artifact to 4.3
Post-Cutover | 3.1 | Runtime Health Check Validation | All 23 BGs | RHEL 9 | DevOps | Y |  | Pending | Check CPU/Heap; Splunk logs; API response test | Switch traffic back to 4.3
Post-Cutover | 3.2 | Business Validation Sign-Off | All 23 BGs | RHEL 9 | Business + DevOps | Y |  | Pending | Confirm all APIs responding 200 OK | Trigger rollback plan